# Project Management and Risks

Plant Disease AI: Development of an AI-Powered Plant Disease Detection and Treatment Recommendation System

Component 10, pre-defense 1 (24 October 2026). Team: Abdullayev Shynggys, Kalen Mukhammedali, Orynbasarov Alikhan. Supervisor: Kydyrbekova Aigerim.

# 1. Repository and task tracker

| Item | Where |
| --- | --- |
| Backend and ML repository | github.com/shaminabd/Plant-Disease-Detection-api (documents in docs/) |
| Frontend repository | github.com/shaminabd/Plant-Disease-Detection-web |
| Task tracker | Qadam board (link in the README). The supervisor approved Qadam as the project tracker, in place of YouTrack named in the course checklist. |
| Tag for this submission | pre-defense-1 (to be created on the commit that is submitted) |

# 2. Git rules and how the project meets them

The table follows the Git repository requirements of the course. The last column is what the team has to show at the pre-defense. It was not checked by the author of this document, who has no access to the repositories; the team confirms each line before submitting.

| Rule | How the project follows it | To show at the pre-defense |
| --- | --- | --- |
| One repository, clear name, same repository throughout | Two repositories (api and web) with names that identify the project | Both links in the README |
| Access for the team, the supervisor and the committee | Access is given on request | Invitation of the supervisor and the committee before 24 October |
| Own accounts, identifiable commit authors | Each member commits from their own account | Git log with three authors |
| README with title, problem, team, scope, status, technologies, tracker link, setup | README sections for each item, including team responsibilities and status table | The README in the repository (version of this package) |
| Structure: source, documents, diagrams, tests, configuration | backend/, frontend/, docs/, diagrams with .puml sources and exports, .env.example, .gitignore | Directory listing |
| No secrets or personal data in the repository | .env.example has placeholders only (NFR-07); datasets and weights are not committed (NFR-16) | Secret scan result (verification plan M13) |
| Progressive commits, not one upload before the defense | Documents are committed one by one with descriptive messages | History with dates before 24 October |
| Task per work item with owner, outcome, criteria, deadline; task ID in branch, commit and pull request | Branch TASK-ID-short-name; commit TASK-ID: message; pull request links the task and says how it was checked | One task traced from board to pull request to deliverable |
| Pull requests with review by another member; main is the reviewed baseline | Every pull request is reviewed by another member (NFR-18) | Pull requests with review comments and later revisions |
| Tag pre-defense-1, not moved later | Tag on the submitted commit | Tag and the submission summary in section 6 |

# 3. Responsibilities

The work is not split by layer. Each member owns one feature and builds it through the AI and data, backend, frontend and tests. Every module has a deputy, and every pull request is reviewed by another member.

|  | Shynggys | Kalen Mukhammedali | Alikhan |
| --- | --- | --- | --- |
| Feature | Diagnosis: dataset split, three CNNs, Grad-CAM, ONNX, POST /diagnose, result screen | Recommendations: knowledge base, RAG, baseline, POST /recommend, advice screen, kk/ru/en texts | Platform: FastAPI, database, authentication, MinIO, history, Docker, CI, field test set |
| Deputy for | Recommendations | Platform | Diagnosis |
| Oct to Dec 2026 | Tech lead (architecture, merges) | Documents and tracker owner | Tests and CI owner |
| Jan to Feb 2027 | Tests and CI owner | Tech lead | Documents and tracker owner |
| Mar to Apr 2027 | Documents and tracker owner | Tests and CI owner | Tech lead |

Documents for pre-defense 1 were written by the team together; each member checks the parts that belong to their feature (requirements, verification plan and architecture).

# 4. Milestones and dependencies

| When | Milestone | Depends on |
| --- | --- | --- |
| 24 Oct 2026 | Pre-defense 1: documents, prototype, repository, tag pre-defense-1 | Supervisor review; Git access for the committee |
| Nov 2026 [p] | Dataset split without leakage; first training of the three CNNs; field test set collected and labelled twice (DR-03, DR-04) | Dataset licences (DR-12); compute for training |
| Nov to Dec 2026 [p] | Knowledge base with a source for every disease class; indexing; lookup-table baseline (FR-34 to FR-37, FR-21) | Permission to use each source; native-speaker review for Kazakh |
| Dec 2026 [p] | Platform skeleton, authentication, history, CI; stubs for /diagnose and /recommend (NFR-15, NFR-18) | Agreed OpenAPI files |
| Jan to Feb 2027 [p] | Real model and RAG connected; PWA; evaluation on the field test set (M1 to M5, M9) | Embedding and LLM choice (technology comparison, section 11) |
| Mar 2027 [p] | End-to-end tests, load test, security checks, usability test with users (M8, M11 to M13) | Test users |
| Apr 2027 [p] | Final work and defense | The dates of pre-defense 2 and the final pre-defense are not announced yet |

Values marked [p] are provisional. Dates of later pre-defenses are added to the README when announced.

# 5. Risk register

Probability (P) and impact (I): L = low, M = medium, H = high. A risk is reviewed at every milestone.

| ID | Risk | P | I | Response | Warning sign and requirement |
| --- | --- | --- | --- | --- | --- |
| R1 | The model works on PlantVillage but fails on field photos | H | H | Train on PlantVillage and field datasets; keep a separate field test set; report the gap; reject low-confidence photos; calibrate confidence | Field accuracy far below validation accuracy. DR-03, FR-08, M1, M2 |
| R2 | Too few labelled field photos, or classes of field datasets do not match the 38 classes | M | H | Map only matching classes; collect own photos with a second reviewer; state which classes are covered | Fewer than a few dozen photos per class. DR-03, DR-04 |
| R3 | Data leakage between training and test | M | H | Saved split file, automatic duplicate check between train and field test, fixed seeds | Check reports an overlap. DR-03, NFR-20 |
| R4 | The advice contains a dosage or a claim without a source (safety) | M | H | Generate only from retrieved passages; refuse if none; show a reference next to every dosage; manual review of all evaluation answers; disclaimer | Unreferenced dosage in review. FR-14 to FR-18, M9 |
| R5 | Kazakh answers are unfaithful or retrieval does not work for Kazakh | M | M | Test embeddings and LLM on kk questions; native-speaker review; translate the query before search if needed; state the limit | Low hit rate for kk. NFR-12, FR-03, M9, M10 |
| R6 | LLM provider is expensive, has limits, or is unavailable | M | M | Provider chosen by configuration; lookup-table fallback; cache of evaluation answers | Quota errors. NFR-17, FR-22, NFR-02 |
| R7 | Knowledge base sources or datasets have licences that forbid use or sharing | M | M | Record licence or permission for each source before use; prefer open guides; ask for permission | Source without a permission note. DR-12, FR-34 |
| R8 | No compute for training or training is too slow | M | M | Fine-tune small pretrained models; free or university GPU time; fewer epochs; compare on a subset first | First run takes more than a day. DR-02 |
| R9 | CPU inference is slower than 10 seconds [p] | M | M | ONNX Runtime, smaller model, image size limit; report the real time | Measured time above the target. NFR-01, M7 |
| R10 | Three people, about six months: scope grows | H | M | MoSCoW priorities; Won't list W-01 to W-08; Should items only if time allows; scope reviewed at milestones | Must items late at a milestone. Requirements section 8 |
| R11 | A team member is absent or work is not balanced | M | M | Deputy for each module; rotating roles; review by another member; tasks visible on the board | Task without activity for two weeks. Section 3 |
| R12 | Personal data or secrets leak | L | H | Minimum data; salted password hashes; private bucket; only text to the LLM; secret scan in CI | Scan finds a key. NFR-06 to NFR-10, M13 |
| R13 | Users do not understand or trust the result | M | M | Plain language; show confidence and top 3; heatmap; sources; usability test | Test users fail the scenario. FR-30, M12 |
| R14 | The repository does not show continuous work | M | M | Commit documents and code as tasks are done; task IDs in branches and pull requests | Few commits before the milestone. Section 2 |

# 6. Submission summary for pre-defense 1

- Completed: proposal, evidence of relevance (3 interviews), literature review (28 sources), comparison of existing systems (hands-on test of 3 apps), technology comparison, requirements specification (69 requirements), architecture and diagrams, UX prototype ÖSIM-AI, verification plan, this document.

- Known limitations: no model is trained yet; the prototype shows fixed examples; Kazakh support of the embedding model and the LLM is still to be tested; the licences of datasets and sources are not yet recorded; target values are provisional [p].

- Outstanding tasks: dataset split and first training; field test set; knowledge base and licence table; platform skeleton and CI; test of embeddings and LLM; supervisor review of the documents.

# 7. Next steps

- Create Qadam tasks for the outstanding work in section 6, each with an owner from section 3, a requirement ID, acceptance criteria and a deadline.

- Create the tag pre-defense-1 after the last merged document change.

- Send the documents to the supervisor and record her comments and the team response (component 11).

- Review the risk register after the supervisor feedback and at every milestone.